## Slide 1: BDC QI Update Adult Clinic Equity Project
January 2025

## Slide 2: BDC: Who Makes Up the Adult Clinic?
- 2,849 unique patients
- 77% privately insured, 20% Government, 2% Military, 1% Self-Pay
- 2% Non-Hispanic Black, 8% Hispanic, 85% White, 5% Other/ Declined to Answer
- 7,236 visits per year
- Providers: 6 MD, 1 NP, 2 PA
- CDCES: 1 social worker, 1 nurse, 3 dieticians
- 2 MA’s
- 1 Person solely responsible for all prior authorizations

## Slide 3: QI Project 2023-2025
Improve access to diabetes technologies for our minority patients
Part of the Equity Team
Increase the amount of Black + Hispanic Patients using CGM’s by 5% by 12/31/2024 (T1D exchange goal is 70%)
Increase the amount of Black + Hispanic Patients using Pumps by 5% by 12/31/2024 (T1D exchange goal is 65%)
*Our AIMS are different than the Equity Team’s to align more realistically with our patient population and how many patients are currently using technology
Disparities for diabetes devices exist EVERYWHERE!
This needs to be a priority for all clinics, insurance companies, and device companies in order to create systematic changes.

## Slide 4: CGM/Pump Process Map – Current patient
Pt attends clinic appointment/Phone call to clinic
Family expresses interest in pump/CGM
Educator comes in clinic room to discuss potential pump/ cgm options and initial training
CDE/Provider ask family if they are interested in pump/CGM
Key:
Process Start
Decision
Education/Discussion
Process
Pt focus
CDE/Provider focus
Has family received pump/CGM education?
Does family know which pump/CGM they would like?
YES
NO
Discuss process on next steps to order pump/CGM and have provider write prescription
NO
YES
RX for CGM sent to appropriate distributor based on insurance
CDE/Provider provides information regarding the different options available and what makes sense for their goals and needs
Family reaches out to pump company to start process
Rx sent to pharmacy
Omnipod 5
Tandem
CGM
YES
NO
CDE/Provider provides ongoing support/education to help family make pump decision. Send them home with samples of Dexcom or libre if they do not have a CGM
Is family interested in pumps/CGMs?
Family begins pump start/ intro guide per omnipod guidelines. They are advised to reach out to the clinic two weeks after start
Once the pump has shipped Tandem or Medtronic will email regarding scheduling training. Patient is advised to contact the clinic 2 weeks after pump start to review.
Pain Point
The patient does not always follow up/ complete training or come back into the clinic for a check-in. Sometimes the clinic is too busy to do pump follow-ups (a new PA is starting who will have a big focus on pump follow-ups)
We do not have a uniform process for checking in with patients in the clinic, with whether or not they want to revisit new tech.
If copay or out of pocket cost is too high, patients do not always follow up
CDE refers patients to diabetes.shop to place their order
Medtronic
Areas of Focus

## Slide 5: Equity Expansion Dashboard- CGM
Chart: BDC Adult CGM Use by Race
| 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139
NHW | 0.76136 | 0.79675 | 0.76241 | 0.75732 | 0.7033 | 0.56809 | 0.79524 | 0.6139 | 0.70463 | 0.8022 | 0.78884 | 0.82463 | 0.74262 | 0.8 | 0.82432 | 0.86268 | 0.80377 | 0.85274 | 0.84553 | 0.8048
NHB | 0.6 | 0.53846 | 0.33333 | 0.5 | 0.5 | 0.54545 | 0.5 | 1 | 0.5 | 0.41667 | 0.71429 | 0.625 | 1 | 0.7 | 0.6 | 0.7 | 0.55556 | 0.55556 | 0.84615 | 0.71429
HIS | 0.36 | 0.7037 | 0.52632 | 0.72414 | 0.5 | 0.525 | 0.5 | 0.64516 | 0.72973 | 0.65517 | 0.61538 | 0.64516 | 0.55 | 0.68966 | 0.5814 | 0.71429 | 0.79412 | 0.71111 | 0.76667 | 0.76087

## Slide 6: Equity Expansion Dashboard- Pump
Chart: BDC Adult Pump Use by Race
| 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139
NHW | 0.70076 | 0.69919 | 0.74823 | 0.74477 | 0.71062 | 0.71984 | 0.75238 | 0.72587 | 0.72242 | 0.74359 | 0.68127 | 0.71642 | 0.73418 | 0.764 | 0.72297 | 0.71479 | 0.75849 | 0.71233 | 0.72358 | 0.72673
NHB | 0.6 | 0.53846 | 0.33333 | 0.375 | 0.66667 | 0.45455 | 0.5 | 0.6 | 0.5 | 0.41667 | 0.28571 | 0.5 | 0.4 | 0.6 | 0.46667 | 0.6 | 0.33333 | 0.33333 | 0.53846 | 0.57143
HIS | 0.48 | 0.51852 | 0.42105 | 0.51724 | 0.57692 | 0.55 | 0.5 | 0.51613 | 0.64865 | 0.55172 | 0.57692 | 0.48387 | 0.55 | 0.65517 | 0.44186 | 0.64286 | 0.61765 | 0.6 | 0.6 | 0.54348

## Slide 7: Statistical Significance
Group Comparisons | White Patient Percentage | Minority Patient Percentage | P- Value
Hispanic vs. White Pump Use | 68% | 53% | p < 0.00001
Non-Hispanic Black vs White Pump Use | 68% | 53% | p = 0.008
Hispanic vs. White CGM Use | 81% | 68% | p < 0.00001
Non-Hispanic Black vs White CGM Use | 81% | 69% | p = 0.014

## Slide 8: PDSA 1- Cycle 1- Asking Everyone if they Want Technology
We needed to decipher what barriers were especially present for our minority patients.
We needed to find the relevant barriers in order to know what to target.
Retrospective chart review to see if all providers are asking all patients without technology if they want to/ are providing these patients education on tech options.
Chart review was not helpful as most providers do not adequately document if they ask the patients. Most notes are general.
Observed some trends in which providers document their tech conversations more than others- address this provider bias? Is it a bias or are they just not documenting?
Approximately 250 chart reviews from 13 NOV2023- 28 NOV2023

## Slide 9: PDSA 2- Ask Patients Directly About Lack of Tech Use
Weekly, identify which of Dr. Akturk’s patients that are coming in are not on devices (not or CGM, pump, or either)
Provide him with this list and have him ask these patients 3 questions regarding if they had previously been asked in they were interested in technology, if they had previously tried technology, or why they were not interested.
Week 1: 10 patients identified
  10 without pumps and 4 without CGM’s
  There is not sufficient time to ask these questions
  Want to focus on just minority patients to ask these questions to
  Proposed starting with one patient

## Slide 10: PDSA 3- EPIC Data Pull
Had Bing do a data pull of Hispanic and Black patients who have been seen in the past year, who do not have a CGM and/ or pump, with their previous A1c, and their next appointment date (if they have one in the next 6 months).
Chart: Device Disparities Data Pull
| No Devices, Not Meeting Goal, Follow up Scheduled | No Devices, Not Meeting Goal, No Follow up Scheduled | No Devices, Meeting Goal
 | 48 | 47 | 33

## Slide 11: PDSA 3/4- Questionnaire
Give the patients not at goal with follow-up scheduled a “Device Disparities Questionnaire” at their visit
“You are receiving this because you are not using a pump and/ or CGM. We want to know what barriers you face in receiving this technology. Please list the top three barriers you experience to not receiving this technology. All information you share is confidential and will not be shared outside of the clinic. This information is not for research and is solely for a quality improvement project so we can better improve the outcomes for patients in our clinic.”
Goal is to see what barriers our patients face in getting devices
See what barriers are most common and find ways to solve/ mitigate those
Did PDSA 3, then we reran the query to caput more patients

## Slide 12: PDSA 3/4- Data Reflection
- 13% response rate
- 43% cancelation (for one reason or another) for this population
- While the questionnaire gave us good information regarding technology barriers, the cancelation and no-show rate for this population was very eye-opening
- Can not get technology if they miss their appointment

## Slide 13: Pareto for Questionnaire Responses
Vital Few
Chart: Barriers to Starting a Pump or CGM
| Nervous about change | Cost | Fear of pump malfunction | Appearance | Fear it will fall off | Insurance inconvenience | Never considered switching | Discomfort | Specific tech concern
 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1
 | 0.22222 | 0.38889 | 0.5 | 0.61111 | 0.72222 | 0.83333 | 0.88889 | 0.94444 | 1

## Slide 14: Address the Vital Few
Nervous about Change
  Education!
  Remind patients we are here to support this change
  Provide resources about where they can go for questions
  Offer alternatives; do not have to start AID immediately, start with just a CGM, then add a pump or insulin pen, then turn on AID
Cost
  While we can not directly change the cost of these products we can still help in a few ways
  Work with the patient and their insurance for what may be the most cost-effective, i.e. going through pharmacy instead of DME
  Coupons available for specific products
  Industry support systems for limiting out-of-pocket cost
Ultimately we should work on focusing our education on these aspects to increase device use in our clinic, especially for minorities.

## Slide 15: CGM Use by Race Now

## Slide 16: Pump Use by Race Now

## Slide 17: Next Steps
PDSA 5: Call patients and discuss what barriers they face to coming to the clinic. We can not discuss technology with patients we can not see. Perhaps there is a barrier here we can address.
Need to test our education for cost and fear of change. Not quite sure the best way to test this. Approach one of the patients that answered that in the questionnaire and have a discussion with them.

## Slide 18: Barriers to Project Success
- High device utilization rate in our clinic
- Predominately white patients
- Lack of buy-in

## Slide 19: Other Ideas to Help
Implement Social Determinants of Health Questionnaire
  Allow us to better understand specific barriers
  Give attention to all patients
  Get a well-rounded idea of a patient’s hardships and concerns and what is impacting their health
  Zoom out from diabetes technology, but also learn about the barriers patients face that may interfere with them being on technology.