## RAIL
2023-08-29 | T1D CGM Equity Project- Rolling Action Item List
AIM: Reduce the inequity of CGM technology access/utilization among White, Hispanic and Black T1D patients
| Key Driver | Intervention | PDSA | Point Person | Progress Note | Next Steps | Next Report T1Dx | Status
| Provider Education | 1. Provide table with Rep information for CGMs and PUMPs. 2. Provide table with specialty pharmacy | Create checklist on method used and time range between order and supplies recieved | Educator | Follow timeline of visit, order method and patient receiving supplies | Create comparison table Note:can include timeline of previous patients who were directly referred to vendor? |  | In progress
| Patient Education | Provide "follow up" steps when reachinng insurance problem | Create steps on troubleshooting (office, pharmacy, DME, vendor) | Educator | Provide education sheet at end of visit | Create suvey to assess functionality |  | In progress

## Sample PDSA #5
PDSA Worksheet Nationwide Children's Hospital Intervention #5
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: |  | 1
Change Idea: | Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity
Test Cycle Start Date | 44531 | Test Completion Date: |  | 44557
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
To Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity we need to: 1. Order data set 2. Segment data by racial populations (table) (pie chart) 3. Compare % by racial population (funnel p-chart) 4. identify racial disparity (if any)
What do you predict will happen in this cycle? (Make sure its realistic)
Our prediction is that there will be little to no disparity in the application of SDH assessments. Hospital initial 2021 goal is 70% assessment rate.
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
STUDY: (to be completed after the test cycle)
Did the results match your prediction? |  |  | 92% average assessment - none outside control limits - little process variation
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Begin tracking SW follow-up with Needs Reported (food, housing, transportation)

## Sample PDSA #11
PDSA Worksheet Nationwide Children's Hospital Intervention #5
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 1
Change Idea: | Standardize clinic uptake process and eliminate “8 wastes” in procedures
Test Cycle Start Date | 44211 | Test Completion Date: | 44593
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
To Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity we need to: 1.Outline Diabetes Nurse Educator preliminary steps 2. Outline Nurse AP standard appointment process for pump initiation 3. Identify any points which may 1) delay implementation; and/or 2) caution bias opportunity 4. Remediate as needed
What do you predict will happen in this cycle? (Make sure its realistic)
Our prediction is that there will be identifiable bias opportunities for caution
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
1/15/2022 Belinda Beth has sent me information for what is done prior to when the AP is involved with scheduling pump start. The steps listed here involve the Diabetes Nurse Educator (DNE) and the Advance Nurse Practitioner 1. Provider approves patient to start the pump process and hands the family the pump class brochure. 2. Family reads the brochure and follows instructions to sign up for the pump class taught by the DNE - language, communication ease 3. After family attends the class, families to complete the Referral form which indicates which pump they want and return to our department via email or MyChart -language 4. DNE who supports the provider last seen signs the referral and gives to the provider for final sign off. 5. Once the provider signs, the DNE completes the CMN to start the ordering process Standardize appt process for pump initiation: 1. Once the pt/family has been approved, signed off to start a pump, they call the pump company. 2. Pump company then contacts insurance and that is all out of our (NCH) hands. 3. Pump company asks us for office visit notes. 4. Once family receives pump(at their home), the pump trainer reaches out to AP’s for open dates to do insulin start according to our schedules. We are doing this in our office time currently (and have for years) but this is about to be changed- to be during the Ap’s clinic time (in a few months because schedules are so full now). 5. The pump trainer then reaches family w potential insulin start dates; saline start is 5-7 days prior to that. 6. Once dates are confirmed with family, trainer and APs, trainer contacts Heather Perry to schedule room for training. At that point in time is when I usually send pump trainer orders for insulin doses to start the pump. 7. We have a smart phrase in EPIC for pump start visit and for pump instructions to give the family. language 8. In the past, we would try to have them back in 2-4 weeks. The way our schedules are (FULL!) that has been impossible. They are instructed to send /upload bgs every 2-3 days (I tell them which days of the week) so we can be aggressive about making changes. We typically decrease their basal insulin to 80% of what it was w/ injections to avoid lows, but this can make them higher than they usually are so may make them feel bad/ have ketones that’s why I tell them we like to be aggressive in the beginning. - language
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
Areas listed above in black text were identified as opportunities for bias in assessment or program delivery. Also translation and transportation support issues
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Work with team at each area/issue to flag for unconscious bias and positive resolution of support issues