## RAIL
T1D Pump Equity Project- Rolling Action Item List
AIM: Reduce the inequity of CGM technology access/utilization among White, Hispanic and Black T1D patients
Key Driver | Intervention | PDSA | Point Person | Progress Note | Next Steps | Next Report T1Dx | Status
Address Inequitities | Provider Bias Training | 1-Chart review/Collect data to present to provider/educator team about pump use rates by race 2-Create education about health inquities with pre/post test, establish provider champion | Candice, Christin, Dr. Alwazeer, Dr. Hsieh | Starting 8/6/23
| Parents-As-Partners Diabetes Group - Patient Barrier Assessment Survey | 1-Establish group with at least one minority group represented 2-Survey patient/family experience | Candice | 10 families identified - send initial contact letter ??Find copy of "patient barrier assessment survey"
| Provide Education Materials in Multiple Languages | Assessment of Cook Childrens-specific materials vs outside resources | ? Educator
Patient Education | Process of making modules for pump "class" | Assess barriers to self-directed online modules vs educator-led pump class | Diabetes Educator | ON HOLD - awaiting approval from system IT department | Future: translating modules into Spanish and Arabic (potential for other languages).
| Virtual Pump Class | Classes held over Zoom; led by diabetes educator; started December 2022 | Diabetes Educators | Increased patient volume in classes Decreased time to pump start with additional classes offerred | COMPLETED
| 1:1 Pump class due to language barrier or family request | Group spanish class? How often? | Diabetes Educators | Spanish speaking families or arabic families are most often needing 1:1
| Increase patient awareness of availiabiltiy and benefits of insulin pump therapy | Clinic survey 8/28-9/1 | Candice/Dr. Hsieh | PDSA 1 complete (provider discussion) | Run PDSA again with other providers Add pump discussion to HFU
Provider Education | Remove bias of specific pump criteria | Create "are you ready for pump therapy? Checklist that describes skills vs criteria. | Stephanie, Candice, Dr. Hsieh, Dr. Cielonko | Remove specific A1c, allow patients to start pump therapy even if they miss bolus. Discuss options for closed loop and meal announcement pumps; tailored to patients with sub-par diabetes habits
Partner with Vendors - Coverage of Omnipod 5 by TX Medicaid | Letter from providers to TX Medicaid to approve OP5 integrated pump by end of 2023 vs OP DASH | 1-Draft letter to Medicaid 2-Draft letter to Omnipod | Stephanie, Dr. Thornton | Letter in progress
Future: Questionaire on "have you accessed CGM or pump in the last week"?

## PDSA #1
PDSA Worksheet Cook Children's Medical Center Intervention #1
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 1
Change Idea: | Assess & Address pump interest at all clinic visits - Provider discussion
Test Cycle Start Date | 2023-08-30 | Test Completion Date: | 2023-09-01
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
1. Identify patients on insulin pump and assess their knowledge of pump benefits 2. Identify patients not on insulin pump and assess reason why 3. After discussion about insulin pump therapy, is the patient now interested in insulin pump 4. If not interested after intervention, assess reason FOR ALL ITEMS: Identify racial & payor disparity
What do you predict will happen in this cycle? (Make sure its realistic)
50% of patient seen in clinic (Total 15) will already use insulin pump 80% of our patients will know about insulin pumps 50% of our patients will be interested after provider discussion
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
10 patients seen in clinic on 8/31/23 by MD and NP 1. 4 patients on pump (4 white; all know pump keeps you in range, 1 thinks it's cool) 2. 6 patients not on oump (1 white, 1 black, 4 hispanic, 5 public insurance; 4 state "no one told them", 4 not interested) 3. Post provider discussion (6 total - 1 interested! 3 still not interested, 2 didnt complete) 4. Post provider discussion why not interested? ("Shots work", "sports...will come off")
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
40% of patients use insulin pump (goal was 50%) 66% of patient not on pump know about insulin pumps (goal was 80%) 16% of patients were interested after provider discussion (goal was 50%)
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
*Change "interest" to awareness" Provider discussion about when to talk about insulin pump therapy (REMOVE UNSPOKEN CRITERIA) Expand to assess other providers