## RAIL
Update 6.8.2022 | 8.3.23 | T1D Equity Project- Rolling Action Item List
AIM: Reduce the inequity of advanced technology access/utilization among White, Hispanic and Black T1D patients
|  | Key Driver | Intervention | PDSA | Point Person | Progress Note | Next Steps | Next Report T1Dx | Status
|  | Improve clinic process for CGM | Standardize discussing CGM regularly at appointments & write rx for patients who want CGM | 1-Plan-Conduct chart reviews to see if rx rates vary by provider. | Katie Noland | Completed chart reviews for 89 patients, did not find variability between providers signing rx for new onset | Engage data science team to examine data more closely by race and ethnicity to see if there are differences. Also consider pulling data by dx duration. (noted data set was not very diverse, expand until more groups are represented)
|  | Getting new onset patients on CGM sooner | Create CGM only education (seperated from Pondering Pumps slides) to allow patients to receive earlier education and providers to feel more comfortable prescribing CGMs earlier | Create CGM PPT and REDCap survey to verify pt understanding | Rachel Dixon | PPT completed | Create survey for CGM information review.
|  | Provider Education for Smartpen | Build on existing relationship with Medtronic Rep to provide education to CDCES (record session for physicians to view later). | 1-Plan- Ask Ron H. (Medtronic) to provide SmartPen education focused on benefits of SmartPen use. | Ron H. Julie K. | Medtronic Rep scheduled for August 8, 2023 | Estabslish and communicate to clinic staff clear process navigating rx & insurace.
|  | Patient Education (SmartPen) | Add SmartPen education for families. | 1-Place SmartPen education in existing "Pondering Pumps" technology education slides. | Andie K. | Completed on 7.17.23 | Compare data regarding SmartPen uptake prior to and following July 17, 2023 to measure impact on uptake.
|  | Address Inequities (SmartPen) | Cover copay for SmartPen for one year | 1-Meet w/pharmacy, legal, Medtronic rep to understand what is needed to use unspent emergency funds to cover $35 copay for families for 1 year. | Katelyn, Dr. Ogden, Ron Hoyler | Waiting for review from legal team