## RAIL
T1D Insulin Pump Equity Project- Rolling Action Item List
AIM: Reduce the inequity of insulin pump technology access/utilization among White, Hispanic and Black T1D patients May 2023
Key Driver | Intervention | PDSA | Point Person | Progress Note | Next Steps | Next Report T1Dx | Status
Address Inequities | Schedule group classes during patient visit at checkout before they leave clinic. |  | Educators | Increased scheduling abilities for pump classes - added patient access reps.
| Offer in person monthly pump class on Saturday morning | Class offered July 22nd. 14 patients attend. 2 no shows. 8 completed pump knowledge test. 2 chose insulin pump - in progress. | Educators |  | Will look at who has completed test/pump 1 month after class and then reach out to families. Next class scheduled August 12.
| Added question regarding interested in discussing insulin pumps to our diabetes interval history form that patients receive at every visit prior to seeing provider | Jan1 - paper form, no reviewed in visit. No workflow. | Educators
|  | Redcap survey to have interval questionnaire built into EPIC - Monday 7/31 went live in EPIC | Educators | Needs workflow for providers and nurses to review with family
| Offer 1:1 in person pump education class for all non english speaking families | June 1st started. 9 patients. 5 completed pump test. 5 chose pump - in progress. | Educators | Called 2 families that had not completed test. Did not read Mychart message or threw away patient materials. Resent test and patient education to families. | Will follow up by end of August.
Patient Education | Provided pump comparison chart from Panther Program with pump class materials. | Started June 1st. | Educators
|  | July 27. Incorporated pump comparison materials into patient education - pump class slides | Educators
Provider Education | Removed requirements needed to start on insulin pump. | May 22, 2023 Created a prepump checklist to be completed in clinic - making sure patient had appropriate knowledge base and materials to start on insulin pump. | Educators | Removed requirement of specific A1C, compliance, time since diagnosis.

## Sample PDSA #5
PDSA Worksheet Nationwide Children's Hospital Intervention #5
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: |  | 1
Change Idea: | Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity
Test Cycle Start Date | 44531 | Test Completion Date: |  | 44557
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
To Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity we need to: 1. Order data set 2. Segment data by racial populations (table) (pie chart) 3. Compare % by racial population (funnel p-chart) 4. identify racial disparity (if any)
What do you predict will happen in this cycle? (Make sure its realistic)
Our prediction is that there will be little to no disparity in the application of SDH assessments. Hospital initial 2021 goal is 70% assessment rate.
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
STUDY: (to be completed after the test cycle)
Did the results match your prediction? |  |  | 92% average assessment - none outside control limits - little process variation
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Begin tracking SW follow-up with Needs Reported (food, housing, transportation)

## Sample PDSA #11
PDSA Worksheet Nationwide Children's Hospital Intervention #5
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 1
Change Idea: | Standardize clinic uptake process and eliminate “8 wastes” in procedures
Test Cycle Start Date | 44211 | Test Completion Date: | 44593
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
To Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity we need to: 1.Outline Diabetes Nurse Educator preliminary steps 2. Outline Nurse AP standard appointment process for pump initiation 3. Identify any points which may 1) delay implementation; and/or 2) caution bias opportunity 4. Remediate as needed
What do you predict will happen in this cycle? (Make sure its realistic)
Our prediction is that there will be identifiable bias opportunities for caution
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
1/15/2022 Belinda Beth has sent me information for what is done prior to when the AP is involved with scheduling pump start. The steps listed here involve the Diabetes Nurse Educator (DNE) and the Advance Nurse Practitioner 1. Provider approves patient to start the pump process and hands the family the pump class brochure. 2. Family reads the brochure and follows instructions to sign up for the pump class taught by the DNE - language, communication ease 3. After family attends the class, families to complete the Referral form which indicates which pump they want and return to our department via email or MyChart -language 4. DNE who supports the provider last seen signs the referral and gives to the provider for final sign off. 5. Once the provider signs, the DNE completes the CMN to start the ordering process Standardize appt process for pump initiation: 1. Once the pt/family has been approved, signed off to start a pump, they call the pump company. 2. Pump company then contacts insurance and that is all out of our (NCH) hands. 3. Pump company asks us for office visit notes. 4. Once family receives pump(at their home), the pump trainer reaches out to AP’s for open dates to do insulin start according to our schedules. We are doing this in our office time currently (and have for years) but this is about to be changed- to be during the Ap’s clinic time (in a few months because schedules are so full now). 5. The pump trainer then reaches family w potential insulin start dates; saline start is 5-7 days prior to that. 6. Once dates are confirmed with family, trainer and APs, trainer contacts Heather Perry to schedule room for training. At that point in time is when I usually send pump trainer orders for insulin doses to start the pump. 7. We have a smart phrase in EPIC for pump start visit and for pump instructions to give the family. language 8. In the past, we would try to have them back in 2-4 weeks. The way our schedules are (FULL!) that has been impossible. They are instructed to send /upload bgs every 2-3 days (I tell them which days of the week) so we can be aggressive about making changes. We typically decrease their basal insulin to 80% of what it was w/ injections to avoid lows, but this can make them higher than they usually are so may make them feel bad/ have ketones that’s why I tell them we like to be aggressive in the beginning. - language
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
Areas listed above in black text were identified as opportunities for bias in assessment or program delivery. Also translation and transportation support issues
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Work with team at each area/issue to flag for unconscious bias and positive resolution of support issues