## Equity RAIL
T1D Equity Project- Rolling Action Item List - Cook Children's | [7 empty] | Updated 3-1-2024
AIM: Reduce the inequity of CGM technology access/utilization among White, Hispanic and Black T1D patients
Key Driver | Intervention | PDSA | Point Person | Progress Note | Next Steps | Next Report T1Dx | Status
Address Inequitities (CGM) | Correct data entry - Working with IT to correct CGM brand value | All fields updated | Susan Candice | Flowsheet changes IN PROGRESS NOW Questionaire update NEXT Corrections to current data - UNKNOWN | -IN PROGRESS! (Candice, Susan)
| Provide Vendor Materials in Multiple Languages at diagnosis | Diabetes educator gives brochure at diagnosis (hosp) and HFU | Every Diabetes Educator | CGM PDSA 1 for Jan 2024 - all new onsets get CGM info at diagnosis; add check box to Day1/Day2 education | Done
Address Inequitities (Pump) | Provider Bias Training | 1-Chart review/Collect data to present to provider/educator team about pump use rates by race 2-Create education about health inquities with pre/post test, establish provider champion 3-Pump Approval Guidance | Candice Stephanie Mouhammad Luke Susan | Starting 8/6/23 Meeting completed - 11/2023 Pump Start Guidance Approved Provider Education in Progress | -Distribute pump start guidance (Susan, READY) -Schedule provider pump ed (Luke)
| Parents-As-Partners Diabetes Group - Patient Barrier Assessment Survey | 1-Establish group with at least one minority group represented 2-Survey patient/family experience | Candice | 10 families identified - send initial contact letter ??Find copy of "patient barrier assessment survey" |  |  | ON HOLD, UNTIL Jan 2024
| Provide Education Materials in Multiple Languages | Assessment of Cook Childrens-specific materials vs outside resources | Candice Stephanie Educators |  | IN PROGRESS, EMAIL TO VENDORS | COMPLETED
Patient Education (Pump) | Process of making modules for pump "class" | Assess barriers to self-directed online modules vs educator-led pump class | Stephanie | IN PROGRESS - awaiting approval from system IT department | Currently building with IT Future: translating modules into Spanish and Arabic (potential for other languages).
| Virtual Pump Class | Classes held over Zoom; led by diabetes educator; started December 2022 | Diabetes Educators | Increased patient volume in classes Decreased time to pump start with additional classes offerred | COMPLETED | COMPLETED
| 1:1 Pump class due to language barrier or family request | Group spanish class? How often? | Diabetes Educators | Spanish speaking families or arabic families are most often needing 1:1 | Currently, 1:1 spanish classes going well. No change for now. | COMPLETED
| Increase patient awareness of availiabiltiy and benefits of insulin pump therapy | Pump PDSA 3 - Complete | Candice Stephanie | PDSA 3 - Success | Getting bundles to 9 satellite clinics | COMPLETED
Partner with Vendors - Coverage of Omnipod 5 by TX Medicaid | Letter from providers to TX Medicaid to approve OP5 integrated pump by end of 2023 vs OP DASH | 1-Draft letter to Medicaid 2-Draft letter to Omnipod | Stephanie, Dr. Thornton | Letter completed and sent |  | COMPLETED

## Pump PDSA #1
PDSA Worksheet Cook Children's Medical Center Intervention #1
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 1
Change Idea: | Assess & Address pump interest at all clinic visits - Provider discussion
Test Cycle Start Date | 2023-08-30 | Test Completion Date: | 2023-09-01
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
1. Identify patients on insulin pump and assess their knowledge of pump benefits 2. Identify patients not on insulin pump and assess reason why 3. After discussion about insulin pump therapy, is the patient now interested in insulin pump 4. If not interested after intervention, assess reason FOR ALL ITEMS: Identify racial & payor disparity
What do you predict will happen in this cycle? (Make sure its realistic)
50% of patient seen in clinic (Total 15) will already use insulin pump 80% of our patients will know about insulin pumps 50% of our patients will be interested after provider discussion
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
10 patients seen in clinic on 8/31/23 by MD and NP 1. 4 patients on pump (4 white; all know pump keeps you in range, 1 thinks it's cool) 2. 6 patients not on pump (1 white, 1 black, 4 hispanic, 5 public insurance; 4 state "no one told them", 4 not interested) 3. Post provider discussion (6 total - 1 interested! 3 still not interested, 2 didnt complete) 4. Post provider discussion why not interested? ("Shots work", "sports...will come off")
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
40% of patients use insulin pump (goal was 50%) 66% of patient not on pump know about insulin pumps (goal was 80%) 16% of patients were interested after provider discussion (goal was 50%)
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
*Change "interest" to awareness" Provider discussion about when to talk about insulin pump therapy (REMOVE UNSPOKEN CRITERIA) Expand to assess other providers
no documented discussion
don’t trust technology
supply
tech issues
not documented
Adapt
Adopt
Abandon
Yes
No

## Pump PDSA #2
PDSA Worksheet Cook Children's Medical Center Intervention #1
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 2
Change Idea:
Test Cycle Start Date | 2024-01-03 | Test Completion Date: | 2024-01-03
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
1. Identify patients on insulin pump and assess their knowledge of pump benefits 2. Identify patients not on insulin pump and assess reason why 3. After discussion about insulin pump therapy, is the patient now interested in insulin pump 4. If not interested after intervention, assess reason 5. GIVE PUMP INFORMATION AS HANDOUT FOR ALL ITEMS: Identify racial & payor disparity
What do you predict will happen in this cycle? (Make sure its realistic)
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
-Create QR handout (Candice and Stephanie)
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
-PDSA 2, 3/6 signed up for pump class, 1/6 accepted info, 2 not interested
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Adapt
Adopt
Abandon
Yes
No

## Pump PDSA #3
PDSA Worksheet Cook Children's Medical Center Intervention #3
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 3
Change Idea: | Using pump bundle information during provider conversation about pump therapy
Test Cycle Start Date | 2/21 and 2/27 | Test Completion Date: | 2024-02-27
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
1. Identify patients on insulin pump and assess their knowledge of pump benefits 2. Identify patients not on insulin pump and assess reason why 3. After discussion about insulin pump therapy, is the patient now interested in insulin pump 4. If not interested after intervention, assess reason 5. GIVE PUMP INFORMATION AS HANDOUT - Now includes larger clinic and payer mix FOR ALL ITEMS: Identify racial & payor disparity
What do you predict will happen in this cycle? (Make sure its realistic)
Increased pump interest/readiness
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
-PDSA 3, 10/12 expressed interest or readiness -Not able to collect data on class sign up -Create QR handout, pending (Candice and Stephanie)
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
Similar to previous PDSA cycles, extending the pump interest survey, the provider conversation, along with using the pump bundle helped majority of patients seen in 2 clinics move forward with pump interest
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Monitor conversion from interest, to class, to pump start
Adapt
Adopt
Abandon
Yes
No

## PUMP Ramp Summary
Ramp Summary
| Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Describe the intent and structure of the test cycle | Identify reasons for lack of pump use; provider introduce pump therapy AFTER VISIT | Provider review insulin pump therapy DURING VISIT | Increase interest in pump therapy
What changed from previous test cycle |  | conversation while in clinic visit | Conversation + pump info bundle during visit
Results: Data and observations | 40% of patients use insulin pump (goal was 50%) 66% of patient not on pump know about insulin pumps (goal was 80%) 16% of patients were interested after provider discussion (goal was 50%) | 3/6 signed up for pump class, 1/6 accepted info, 2 not interested | -PDSA 3, 10/12 expressed interest or readiness
Action Adapt/Adopt/Abandon | ADOPT | ADOPT/ADAPT | ADOPT

## CGM PDSA #1
PDSA Worksheet Cook Children's Medical Center Intervention #1
Project Title: | Improving T1D Healthcare Equity- CGM | Test Cycle Number: | 1
Change Idea:
Test Cycle Start Date |  | Test Completion Date:
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
What do you predict will happen in this cycle? (Make sure its realistic)
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
STUDY: (to be completed after the test cycle)
Did the results match your prediction?
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Adapt
Adopt
Abandon
Yes
No

## CGM Ramp Summary
Ramp Summary
| Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Describe the intent and structure of the test cycle
What changed from previous test cycle
Results: Data and observations
Action Adapt/Adopt/Abandon

## PDSA #5 (hidden)
PDSA Worksheet Nationwide Children's Hospital Intervention #5
Project Title: | Improving T1D Healthcare Equity- Insulin Pump | Test Cycle Number: | 1
Change Idea: | Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity
Test Cycle Start Date | 2021-12-01 | Test Completion Date: | 2021-12-27
PLAN (to be completed before the test cycle)
Describe the intent and structure of the test cycle: What are you trying to accomplish? Action steps to carry out the test cycle (who, what, where & when) What are you predicting?
To Identify insulin pump users % SDH assessment Jan-Nov 2021 and compare racial populations for disparity we need to: 1. Order data set 2. Segment data by racial populations (table) (pie chart) 3. Compare % by racial population (funnel p-chart) 4. identify racial disparity (if any)
What do you predict will happen in this cycle? (Make sure its realistic)
Our prediction is that there will be little to no disparity in the application of SDH assessments. Hospital initial 2021 goal is 70% assessment rate.
DO: (to be completed after the test cycle)
What happened? Describe your observations and data. Was there anything that occurred that was not part of the plan?
STUDY: (to be completed after the test cycle)
Did the results match your prediction? |  | 92% average assessment - none outside control limits - little process variation
How did the results compare to your prediction? Was the process efficient? Did you encounter unexpected effects? What where your general observations? What did you learn?
ACT: (to be completed after the test)
Debrief with the team and decide on next steps based on what you observe from the study phase
Begin tracking SW follow-up with Needs Reported (food, housing, transportation)
Adapt
Adopt
Abandon
Yes
No