## Slide 1: BDC QI Update Adult Clinic
June 2024

## Slide 2: BDC: Who Makes Up the Adult Clinic?
- From June 2023- June 2024
- 2,849 unique patients
- 77% privately insured, 20% Government, 2% Military, 1% Self-Pay
- 2% Non-Hispanic Black, 8% Hispanic, 85% White, 5% Other/ Declined to Answer
- 7,236 visits per year
- Providers: 6 MD, 1 NP, 2 PA
- CDCES: 1 social worker, 1 nurse, 3 dieticians
- 2 MA’s
- 1 Person solely responsible for all prior authorizations

## Slide 3: Baseline Data
Race_Ethnicity | #OfPts_Total | #OfPts_OnPump_LastVisit | #OfPts_OnCGM_LastVisit | A1c_Avg_11012021To11172023 (%)
Hispanic | 267 | 143 | 181 | 7.92
Non-Hispanic Black | 68 | 36 | 47 | 8.44
Non-Hispanic White | 2453 | 1672 | 1987 | 7.22
- Patients seen at BDC Adult clinic between 11/1/2021 and 11/17/2023 (office visit or telehealth). - CGM and pump uses are determined by the EPIC flowsheet values from the most recent visit, up to 11/17/2023. - Average A1cs are calculated from all A1c values with result dates between 11/1/2021 and 11/17/2023.

## Slide 4: CGM/Pump Process Map – Current patient
Pt attends clinic appointment/Phone call to clinic
Family expresses interest in pump/CGM
Educator comes in clinic room to discuss potential pump/ cgm options and initial training
CDE/Provider ask family if they are interested in pump/CGM
Key:
Process Start
Decision
Education/Discussion
Process
Pt focus
CDE/Provider focus
Has family received pump/CGM education?
Does family know which pump/CGM they would like?
YES
NO
Discuss process on next steps to order pump/CGM and have provider write prescription
NO
YES
RX for CGM sent to appropriate distributor based on insurance
CDE/Provider provides information regarding the different options available and what makes sense for their goals and needs
Family reaches out to pump company to start process
Rx sent to pharmacy
Omnipod 5
Tandem
CGM
YES
NO
CDE/Provider provides ongoing support/education to help family make pump decision. Send them home with samples of Dexcom or libre if they do not have a CGM
Is family interested in pumps/CGMs?
Family begins pump start/ intro guide per omnipod guidelines. They are advised to reach out to the clinic two weeks after start
Once the pump has shipped Tandem or Medtronic will email regarding scheduling training. Patient is advised to contact the clinic 2 weeks after pump start to review.
Pain Point
The patient does not always follow up/ complete training or come back into the clinic for a check-in. Sometimes the clinic is too busy to do pump follow-ups (a new PA is starting who will have a big focus on pump follow-ups)
We do not have a uniform process for checking in with patients in the clinic, with whether or not they want to revisit new tech.
If copay or out of pocket cost is too high, patients do not always follow up
CDE refers patients to diabetes.shop to place their order
Medtronic
Areas of Focus

## Slide 5: Equity Expansion Dashboard- CGM
Chart: BDC Adult CGM Use by Race
| 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139
NHW | 0.76136 | 0.79675 | 0.76241 | 0.75732 | 0.7033 | 0.56809 | 0.79524 | 0.6139 | 0.70463 | 0.8022 | 0.78884 | 0.82463 | 0.74262 | 0.8 | 0.82432 | 0.86268 | 0.80377 | 0.85274 | 0.84553 | 0.8048
NHB | 0.6 | 0.53846 | 0.33333 | 0.5 | 0.5 | 0.54545 | 0.5 | 1 | 0.5 | 0.41667 | 0.71429 | 0.625 | 1 | 0.7 | 0.6 | 0.7 | 0.55556 | 0.55556 | 0.84615 | 0.71429
HIS | 0.36 | 0.7037 | 0.52632 | 0.72414 | 0.5 | 0.525 | 0.5 | 0.64516 | 0.72973 | 0.65517 | 0.61538 | 0.64516 | 0.55 | 0.68966 | 0.5814 | 0.71429 | 0.79412 | 0.71111 | 0.76667 | 0.76087

## Slide 6: Equity Expansion Dashboard- Pump
Chart: BDC Adult Pump Use by Race
| 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139
NHW | 0.70076 | 0.69919 | 0.74823 | 0.74477 | 0.71062 | 0.71984 | 0.75238 | 0.72587 | 0.72242 | 0.74359 | 0.68127 | 0.71642 | 0.73418 | 0.764 | 0.72297 | 0.71479 | 0.75849 | 0.71233 | 0.72358 | 0.72673
NHB | 0.6 | 0.53846 | 0.33333 | 0.375 | 0.66667 | 0.45455 | 0.5 | 0.6 | 0.5 | 0.41667 | 0.28571 | 0.5 | 0.4 | 0.6 | 0.46667 | 0.6 | 0.33333 | 0.33333 | 0.53846 | 0.57143
HIS | 0.48 | 0.51852 | 0.42105 | 0.51724 | 0.57692 | 0.55 | 0.5 | 0.51613 | 0.64865 | 0.55172 | 0.57692 | 0.48387 | 0.55 | 0.65517 | 0.44186 | 0.64286 | 0.61765 | 0.6 | 0.6 | 0.54348

## Slide 7: Hispanic Tech Use 12/6/2023
Hispanic Pump: 53%
Hispanic CGM: 68%
Chart: 
| Number of Patients Total | Number of Patients on a Pump at Their Last Visit | Number of Patients on a CGM at Their Last Visit
Hispanic | 267 | 143 | 181

## Slide 8: Non-Hispanic Black Tech Use 12/6/2023
Non- Hispanic Black Pump: 53%
Non- Hispanic Black CGM: 69%
Chart: 
| Number of Patients Total | Number of Patients on a Pump at Their Last Visit | Number of Patients on a CGM at Their Last Visit
Non-Hispanic Black | 68 | 36 | 47

## Slide 9: Non-Hispanic White Tech Use 12/6/2023
Non- Hispanic White Pump: 68%
Non- Hispanic White CGM: 81%
Chart: 
| Number of Patients Total | Number of Patients on a Pump at Their Last Visit | Number of Patients on a CGM at Their Last Visit
Non-Hispanic White | 2453 | 1672 | 1987

## Slide 10: Statistical Analysis on Race Gap in Tech Use
- Hispanic vs. White Pump Use: p < 0.00001
- Non-Hispanic Black vs White Pump Use: p = 0.008, p < 0.05
- All Minorities vs White Pump Use: p < 0.00001
- Hispanic vs. White CGM Use: p < 0.00001
- Non-Hispanic Black vs White CGM Use: p = 0.014, p < 0.05
- All Minorities vs White CGM Use: p < 0.00001
In all scenarios, there is a statistically significant amount of white patients on technology compared to minorities in our clinic.

## Slide 11: PDSA 1- Cycle 1- Asking Everyone if they Want Technology
Retrospective chart review to see if all providers are asking all patients without technology if they want to/ are providing these patients education on tech options
Chart review was not helpful as most providers do not adequately document if they ask the patients. Most notes are general.
Observed some trends in which providers document their tech conversations more than others- address this provider bias? Is it a bias or are they just not documenting
Approximately 250 chart reviews from 13 NOV2023- 28 NOV2023

## Slide 12: PDSA 2- Ask Patients Directly About Lack of Tech Use
Weekly, identify which of Dr. Akturk’s patients that are coming in are not on devices (not or CGM, pump, or either)
Provide him with this list and have him ask these patients 3 questions regarding if they had previously been asked in they were interested in technology, if they had previously tried technology, or why they were not interested.
Week 1: 10 patients identified
  10 without pumps and 4 without CGM’s
  There is not sufficient time to ask these questions
  Want to focus on just minority patients to ask these questions to
  Proposed starting with one patient

## Slide 13: PDSA 3- EPIC Data Pull
Had Bing do a data pull of Hispanic and Black patients who have been seen in the past year, who do not have a CGM and/ or pump, with their previous A1c, and their next appointment date (if they have one in the next 6 months).
Chart: Device Disparities Data Pull
| No Devices, Not Meeting Goal, Follow up Scheduled | No Devices, Not Meeting Goal, No Follow up Scheduled | No Devices, Meeting Goal
 | 48 | 47 | 33

## Slide 14: PDSA 3- Questionairre
Give the patients not at goal with follow-up scheduled a “Device Disparities Questionnaire” at their visit
“You are receiving this because you are not using a pump and/ or CGM. We want to know what barriers you face in receiving this technology. Please list the top three barriers you experience to not receiving this technology. All information you share is confidential and will not be shared outside of the clinic. This information is not for research and is solely for a quality improvement project so we can better improve the outcomes for patients in our clinic.”
Goal is to see what barriers our patients face in getting devices
See what barriers are most common and find ways to solve/ mitigate those

## Slide 15: PDSA 3- Reflection
Many cancellations- both the clinic and patients canceling around the holidays
The clinic was closed for three days over the holidays
We received a new spreadsheet of upcoming patient appointments to reflect the reschedules. Hopefully this will allow us to capture more data

## Slide 16: PDSA 4- New EPIC Query
Run a new query in Epic to obtain the next scheduled visits of these patients. This captures all of the rescheduled patients we missed in December and January.
72/130 of the patients from this query do not have their next appointment scheduled.
33/130 of the patients in this query are meeting A1c goals.
16/33 of the patients meeting goals do not have a follow-up scheduled
66/97 of patients not meeting A1c goals do not have a follow-up scheduled

## Slide 17: PDSA 3/4- Data Reflection
From 07DEC2023- 19APR2024, 60 patients were identified who fit our criteria for handing out these questionnaires to
5/60 had gotten a pump since their last appointment- did not fill out the questionnaire
5/60 switched to telemedicine- did not fill out the questionnaire
5/60 were no-shows- did not fill out the questionnaire
8/60 filled out the questionnaire
15/60 patients cancelled
6/60 clinic cancelled
2/60 rescheduled
14/60 clinic did not hand out the questionnaire- too busy, forgot, Emma OOO- no backups.

## Slide 18: PDSA 4- Data Reflection
- 13% response rate
- 43% cancelation (for one reason or another) for this population
- While the questionnaire gave us good information regarding technology barriers, the cancelation and no-show rate for this population was very eye-opening
- Can not get technology if they miss their appointment

## Slide 19: Pareto for Questionnaire Responses
Vital Few
Chart: Barriers to Starting a Pump or CGM
| Nervous about change | Cost | Fear of pump malfunction | Appearance | Fear it will fall off | Insurance inconvenience | Never considered switching | Discomfort | Specific tech concern
 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1
 | 0.22222 | 0.38889 | 0.5 | 0.61111 | 0.72222 | 0.83333 | 0.88889 | 0.94444 | 1

## Slide 20: Address the Vital Few
Nervous about Change
  Education!
  Remind patients we are here to support this change
  Provide resources about where they can go for questions
  Offer alternatives; do not have to start AID immediately, start with just a CGM, then add a pump or insulin pen, then turn on AID
Cost
  While we can not directly change the cost of these products we can still help in a few ways
  Work with the patient and their insurance for what may be the most cost-effective, i.e. going through pharmacy instead of DME
  Coupons available for specific products
  Industry support systems for limiting out-of-pocket cost
Ultimately we should work on focusing our education on these aspects to increase device use in our clinic, especially for minorities.

## Slide 21: Next Steps
PDSA 5: Call patients and discuss what barriers they face to coming to the clinic. We can not discuss technology with patients we can not see. Perhaps there is a barrier here we can address.
Need to test our education for cost and fear of change. Not quite sure the best way to test this. Approach one of the patients that answered that in the questionnaire and have a discussion with them.

## Slide 22: Provider Responses to This Project
Our technology rates are already high
I do not have time for this
This is not a race issue/ we mostly see white people
The patient does not care about their health/does not care to learn
The patient can not learn how to use the technology (older patients)
These are adults, we do not need to baby them (should not have to call them to schedule their training, they should be able to read directions and call us)
These remarks are concerning.
By-in from clinicians and the clinic remains a barrier.