## Slide 1: T1D Insulin Pump/InPen Equity Project

## Slide 2: Fishbone

## Slide 3
Provider reviews and signs
PrePump checklist and gives to care coordinator
Care coordinator reviews checklist and provides any needed education, signs checklist and puts checklist in nurse educator folder
Education needs completed
Provider identifies or patient expresses interest in clinic about starting on an insulin pump
Care Coordinator charts using .prepumpchecklist and gives patient pump class packet (In clean utility)
Translation services needed?
Would patient benefit from in-person education?
Yes
No
Yes
No
No
Yes
Insulin Pump process map
Care coordinator instructs family to schedule a RN education appointment at checkout
Patient attends in-person pump class with translation. Pump options discussed
Patient attends in-person pump class. Pump options discussed
Patient attends Zoom pump class. Pump options discussed
Knowledge assessment completed with passing result and patient knows what pump they would like
Referred for further education
No
Omnipod
Tandem, Medtronic or iLet
Prescription sent to pharmacy
Order entered into parachute
Is patient 18 years or older?
Is patient a candidate for self paced education?
Self paced packet given

## Slide 4: PDSA Cycle #1: 1:1 classes for non-English speaking families
  June 2023
  1:1 in person 1:1 Zoom class
  7 patients attended 4 patients attended
  3 patients chose pumps 3 patients chose pump
  July 2023
  1:1 in person
  4 patients attended
  3 patients chose pumps
  August 2023
  1:1 in person
  2 patients attended
  2 patients chose pump

## Slide 5: PDSA Cyle #2: In Person Monthly Weekend Classes
  July 2023
  14 patients attended class
  7 patients chose pump
  August 2023
  9 patients attended class
  3 patients chose a pump

## Slide 6: PDSA Cycle #3 Increase class size for Zoom pump classes
June 2023
13 patients attended class
9 patients chose a pump
July 2023
15 patients attended class
9 patients chose a pump
August 2023
18 patients attended class
7 patients chose a pump

## Slide 7: PDSA Cycle #3
Comments reported back from survey sent to families who have not moved forward on pump therapy.
I am still deciding next steps.
Phil takes mixed martial arts and the pump will be kicked. He teaches for 4 hours
The process of moving forward with pump therapy is too overwhelming.
I am still deciding next steps.
I would like to move forward but I forgot next steps.

## Slide 8: Learning Pearls & Next Steps
We have more patients attending pump class, but less moving forward with pump therapy
Calling patients that attended pump classes to see why they didn't move forward with pump therapy

## Slide 10
Address Inequities

## Slide 11: PDSA #1 (18+): January 2024
Patients >18 years referred to pump class are not deciding on a pump within 3 months of referral
  August 2023: 4 referred, 0 decided on pump therapy
  September 2023: 6 referred, 0 decided on pump therapy
  October 2023: 9 referred, 3 decided
Plan: 1/1/2024: Identify 4 patients > 18 years and have them complete a self-guided packet.
Do:
  4 patients given self-guided packet
Study:
  2 patients let us know that the QR code that takes them to the knowledge assessment doesn't work
  As of 2/1/2024, 2 patients completed packet and decided on pump. 2 patients have not completed the packet
Act:
  Get rid of the QR code
  Attach knowledge assessment questionnaire to a MyChart message that is sent to the patient when they are referred to self-guided tract

## Slide 12: Pump class data May 2023-October 2023
 | Referred | No show | Did not complete process | Decided on pump within 3 month
Number of patients | 186 | 24 (13%) | 75 (40%) | 103(55%)
A1C %(mean) | 9.2% | 9.1% | 8.8% | 8.8%
Age < 5 years | 22 | 1 (4%) | 9 (41%) | 14 (63%)
Age 6-12 years | 65 | 6 (9%) | 24 (37%) | 39 (60%)
Age 13-17 years | 61 | 8 (13%) | 26 (43%) | 34(56%)
Age > 18 years | 38 | 9 (24%) | 16 (42%) | 15 (39%)
White | 110 | 9 (8%) | 41 (37%) | 72(65%)
Hispanic | 31 | 6 (19%) | 16 (52%) | 10(32%)
Non-Hispanic black | 24 | 5 (21%) | 12 (50%) | 9 (38%)
Other | 21 | 4 (19%) | 6 (29%) | 11 (52%)
English speaking | 154 | 22 (14%) | 59 (38%) | 85 (55%)
Non English speaking | 32 | 2 (6%) | 16 (50%) | 16 (50%)
Privately insured | 81 | 4 (5%) | 33 (41%) | 43 (53%)
Publicly insured | 105 | 20 (19%) | 42 (40%) | 43 (41%)

## Slide 13: August 2023 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 27 | 12 (44%)
A1C %(mean) | 9.4 | 9.3
Age < 5 years | 4 | 2
Age 6-12 years | 6 | 2
Age 13-17 years | 12 | 7
Age > 18 years | 4 | 0 (0%)
White | 16 | 7
Hispanic | 5 | 2
Non-Hispanic black | 5 | 3 (60%)
Other | 1 | 0
English speaking | 25 | 12
Non English speaking | 2 | 0 (0%)
Privately insured | 12 | 7
Publicly insured | 15 | 5

## Slide 14: September 2023 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 23 | 11 (48%)
A1C %(mean) | 9.1 | 9
Age < 5 years | 3 | 2
Age 6-12 years | 4 | 3
Age 13-17 years | 9 | 5
Age > 18 years | 6 | 0 (0%)
White | 11 | 7
Hispanic | 4 | 1
Non-Hispanic black | 5 | 2 (40%)
Other | 3 | 1
English speaking | 17 | 9
Non English speaking | 6 | 2 (33%)
Privately insured | 9 | 6
Publicly insured | 14 | 5

## Slide 15: October 2023 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 21 | 10 (48%)
A1C %(mean) | 9.3 | 8.9
Age < 5 years | 1 | 0
Age 6-12 years | 5 | 3
Age 13-17 years | 6 | 4
Age > 18 years | 9 | 3 (33%)
White | 14 | 9
Hispanic | 3 | 0
Non-Hispanic black | 4 | 1 (25%)
Other | 0 | 0
English speaking | 19 | 9
Non English speaking | 2 | 1 (50%)
Privately insured | 8 | 5
Publicly insured | 13 | 5

## Slide 16: November 2023 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 21 | 9 (43%)
A1C %(mean) | 8.7 | 8.1
Age < 5 years | 2 | 1
Age 6-12 years | 9 | 4
Age 13-17 years | 8 | 4
Age > 18 years | 2 | 0
White | 11 | 5
Hispanic | 5 | 2
Non-Hispanic black | 1 | 0
Other | 4 | 2
English speaking | 14 | 5
Non English speaking | 7 | 4
Privately insured | 10 | 5
Publicly insured | 11 | 4

## Slide 17: Update 5/3/2024

## Slide 18: December 2023 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 22 | 8 (36%)
A1C %(mean) | 10 | 10.1
Age < 5 years | 1 | 1
Age 6-12 years | 3 | 3
Age 13-17 years | 13 | 3
Age > 18 years | 5 | 1 (20%)
White | 12 | 6
Hispanic | 2 | 0
Non-Hispanic black | 4 | 1 (25%)
Other | 4 | 1
English speaking | 19 | 8
Non English speaking | 3 | 0
Privately insured | 11 | 5
Publicly insured | 11 | 3

## Slide 19: January 2024 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 28 | 16 (57%)
A1C %(mean) | 8.8 | 9.4
Age < 5 years | 4 | 2
Age 6-12 years | 8 | 7
Age 13-17 years | 6 | 4
Age > 18 years | 10 | 3 (30%)
White | 17 | 8
Hispanic | 7 | 6
Non-Hispanic black | 1 | 1
Other | 3 | 1
English speaking | 24 | 12
Non English speaking | 4 | 4
Privately insured | 14 | 9
Publicly insured | 14 | 7

## Slide 20: February 2024 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 24 | 11 (46%)
A1C %(mean) | 9.6 | 9.7
Age < 5 years | 4 | 1
Age 6-12 years | 6 | 3
Age 13-17 years | 11 | 7
Age > 18 years | 3 | 0
White | 8 | 4
Hispanic | 10 | 5
Non-Hispanic black | 3 | 2
Other | 3 | 1
English speaking | 21 | 10
Non English speaking | 3 | 1
Privately insured | 9 | 5
Publicly insured | 15 | 6

## Slide 21: March 2024 Pump referral data
 | Referred | Decided on pump within 3 month
Number of patients | 24 | 11 (46%)
A1C %(mean) | 9.6% | 9.7%
Age < 5 years | 4 | 1
Age 6-12 years | 6 | 3
Age 13-17 years | 11 | 7
Age > 18 years | 3 | 0
White | 8 | 4
Hispanic | 10 | 4
Non-Hispanic black | 3 | 2
Other | 3 | 1
English speaking | 21 | 10
Non English speaking | 3 | 1
Privately insured | 9 | 5
Publicly insured | 15 | 6

## Slide 23: Next intervention
Calling patients 2 weeks after attending pump class to follow up and identify any barriers, reasons why not moving forward or completing process
Continue our class schedule

## Slide 24: InPen Equity Project

## Slide 25: InPen Fishbone

## Slide 26
Provider/RN sends RX to Alto Pharmacy
Patient/ Provider recommends InPen in visit
RX for insulin cartridges, pen needles sent to local pharmacy
RCHSD InPen PROCESS
= pain point
Prior to education:
family to review in pen tip sheet
Download InPen app
If using dexcom, family to open Apple Health App and add Dexcom and InPen programs
RN faxes signed InPen order form with provider signature and patient face sheet
Instruct families not to request insulin cartridges from pharmacy until InPen is shipped or have in hand.
Public insurance
YES
YES
Family to schedule RN education
Private insurance
Need to send RX to pharmacy for denial
PA sometimes needed from Pharm Tech

## Slide 27: Education with Medtronic reps
Establish rapport with our reps
Process of ordering/education
Discuss having InPen samples in clinic (future PDSA cycle)

## Slide 28: We need data!!

## Slide 29: PDSA Cycle #1
We added a few slides on InPen to our pump education class
We added an insulin delivery device comparison chart in our exam rooms

## Slide 30: Insulin Delivery Devices: Comparison of Features
 | Syringe & Vial | Insulin Pen | InPen | Insulin Pump
Visibility |  |  |  | 
Smallest deliverable unit | 0.5 units | 0.5 units | 0.5 units | 0.05 units
Number of injections in a day | 2-4 | 3-4 | 3-4 | Every 2-7 days
Compatible with CGM |  |  |  | 
Link to phone |  |  |  | 
Bolus calculator |  |  |  | 
Insulin reminders |  |  |  | 
Data viewing |  |  |  | 
Tandem,
Omnipod (not iPhone)
Nothing worn on body
Nothing worn on body
Nothing worn on body
Pod or infusion set connected to pump

## Slide 31: Next steps

## Slide 32: Next Steps
CKC population
Newly diagnosed inpatient
Inpen samples in clinic

## Slide 33: New Process Map
Updated process map
Received samples
Have Humalog cartridge samples

## Slide 34
T1D InPen Equity Project- Rolling Action Item List |  |  |  |  |  |  | 
AIM: Reduce the inequity of in InPen technology access/utilization among White and Black T1D patients |  |  |  |  |  |  | 
Key Driver | Intervention | PDSA | Point Person | Progress Note | Next Steps | Next Report T1Dx | Status
Provider/Nurse Education | Literature review | Present information to providers about benefits of smartpens at division meeting | Anna/Carla - division meeting | Information on InPen process needs to be presented to providers via email/division meeting | Once the process is finalized present to the team |  | 
 | Develop InPen in clinic sample process |  | Kim | 2/1/2024: Process map made for inPen samples in clinic made |  |  | 
 |  |  | Christy | Met with Medtronic representatives 9/21/2023. Received information on InPen process and samples in clinic | Finalize InPen process with step by step information for patients and families - waiting on Medtronic to update contact information |  | 
Partnership with Medtronic | Requested data for outcomes |  |  | Medtronic unable to get us data- pulled articles from T1D exchange |  |  | 
 | call pharmacy to see if they carry cartridges |  |  | our inpatient pharmacy does not carry inpen cartridges |  |  | 
 | Set up meeting with Luke and Medtronic to understand process and resources |  |  |  |  |  | 
 | Meeting with Medtronic 12/13/23 Luke and Melanie to inquire about direct purchase of InPens to provide for patients |  | Christy/Carla | Medtronic has relationship with Novo Nordisk to provide cartridge samples. Will need to speak with Eli Lilly rep for Humalog samples | Carly to meet with NovoNordisk to get samples of Novolog/Fiasp for clinic |  | 
Address inequities | Request baseline data for InPen |  | Carla | 10/6/23 - Carla to ask IT analyst for baseline data - pulling data from Medication list | 1/18/2024: Carla asking for data with MDI and NPH |  | 
 | Health Fair - Medtronic 11/18/2023 |  |  |  |  |  | 
 | Pay the $35 copay for patients who are denied the InPen | Set up account with Express RX | Christy | Utilizing basic needs funds to cover $35 copay for patients who are denied by insurance |  |  | 
RN education | January 5th- Melanie to provide education to RN group re InPen use |  |  |  | Work with Care navigation to identify patients |  | 
Patient education | Add Inpen to contact list to pump book 1/18/24 |  |  |  |  |  | 
 | Add Inpen brochure to pump packets 1/18/24 |  |  |  |  |  | 
 | Added InPen slide to our pump class to offer an additonal technology if pump therapy is not for them | Added to pump class on 10/10/23 | Educators |  | Look at 2-3 patients and assess who made change from sample pen to year-long pens within 30 days. |  | 

## Slide 35: Next Steps
Obtain samples from NovoNordisk
Create account with Express RX
Finalize InPen process
Update Team on process
3 patients identified wanting InPen from pump class

## Slide 36: 4/5/2024 Updates

## Slide 39: Update 5/3/2024 - InPen

## Slide 41: Next Steps
Follow up with patients who have chosen InPen to identify any barriers
Review data on how many of our patients are using InPen to develop baseline

## Slide 42: Update 6/7/2024 - Pump

## Slide 43: Interventions & Results:
Chart: Percentage
| 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45039 | 45069 | 45100 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383
P | 0.24779 | 0.25316 | 0.22388 | 0.33 | 0.21359 | 0.31111 | 0.3 | 0.28261 | 0.17284 | 0.34694 | 0.33673 | 0.26923 | 0.32576 | 0.41026 | 0.30233 | 0.4086 | 0.38889 | 0.31579 | 0.46847 | 0.392 | 0.42188 | 0.46729 | 0.46094 | 0.47445 | 0.54887 | 0.45536 | 0.49474 | 0.48305 | 0.38017 | 0.46479 | 0.51449
+2 Sigma | 0.36641 | 0.38299 | 0.39169 | 0.37174 | 0.37042 | 0.37661 | 0.36755 | 0.37557 | 0.38174 | 0.37265 | 0.37265 | 0.36999 | 0.36008 | 0.4711 | 0.46592 | 0.46194 | 0.46359 | 0.45229 | 0.55862 | 0.55316 | 0.55211 | 0.56037 | 0.55211 | 0.54916 | 0.55044 | 0.5582 | 0.56628 | 0.55577 | 0.55462 | 0.54765 | 0.54885
+1 Sigma | 0.32409 | 0.33238 | 0.33673 | 0.32675 | 0.32609 | 0.32919 | 0.32466 | 0.32867 | 0.33175 | 0.32721 | 0.32721 | 0.32588 | 0.32092 | 0.41668 | 0.41409 | 0.4121 | 0.41292 | 0.40727 | 0.51128 | 0.50855 | 0.50803 | 0.51216 | 0.50803 | 0.50656 | 0.50719 | 0.51107 | 0.51512 | 0.50986 | 0.50929 | 0.5058 | 0.5064
Average | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.28177 | 0.36226 | 0.36226 | 0.36226 | 0.36226 | 0.36226 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395 | 0.46395
-1 Sigma | 0.23945 | 0.23115 | 0.22681 | 0.23678 | 0.23744 | 0.23435 | 0.23888 | 0.23487 | 0.23178 | 0.23633 | 0.23633 | 0.23766 | 0.24261 | 0.30783 | 0.31043 | 0.31241 | 0.31159 | 0.31724 | 0.41662 | 0.41934 | 0.41987 | 0.41574 | 0.41987 | 0.42134 | 0.42071 | 0.41683 | 0.41278 | 0.41804 | 0.41861 | 0.4221 | 0.4215
-2 Sigma | 0.19713 | 0.18054 | 0.17185 | 0.1918 | 0.19312 | 0.18693 | 0.19598 | 0.18797 | 0.1818 | 0.19088 | 0.19088 | 0.19354 | 0.20346 | 0.25341 | 0.2586 | 0.26257 | 0.26093 | 0.27222 | 0.36928 | 0.37474 | 0.37579 | 0.36753 | 0.37579 | 0.37874 | 0.37746 | 0.3697 | 0.36162 | 0.37213 | 0.37328 | 0.38025 | 0.37905
Goal | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
UCL | 0.40873 | 0.43361 | 0.44665 | 0.41673 | 0.41475 | 0.42403 | 0.41045 | 0.42247 | 0.43172 | 0.4181 | 0.4181 | 0.41411 | 0.39923 | 0.52553 | 0.51775 | 0.51178 | 0.51425 | 0.49731 | 0.60595 | 0.59776 | 0.59619 | 0.60858 | 0.59619 | 0.59177 | 0.59368 | 0.60532 | 0.61745 | 0.60168 | 0.59996 | 0.5895 | 0.59131
LCL | 0.15481 | 0.12993 | 0.11689 | 0.14681 | 0.14879 | 0.13951 | 0.15309 | 0.14106 | 0.13181 | 0.14544 | 0.14544 | 0.14943 | 0.1643 | 0.19899 | 0.20677 | 0.21273 | 0.21026 | 0.2272 | 0.32195 | 0.33013 | 0.33171 | 0.31932 | 0.33171 | 0.33613 | 0.33422 | 0.32258 | 0.31045 | 0.32622 | 0.32794 | 0.3384 | 0.33659
Notes: Notes:
-August 2022: OP5 released to market. Many patients who were waiting for this to come out started on it thereafter.

## Slide 44: InPen update 7/5/24

## Slide 45: Patient #1 13y, F, Race – other, public insurance
Attended pump class in April - reached out and requested InPen first before starting OP5. CMN started at that time. Took about 10 days for completed CMN to be faxed to Medtronic.
June – mom sent TDD - sent settings to Medtronic. Mom reports no word on InPen. Sent message to Medtronic re: status - CMN was received but sent to Las Vegas team???
Patient cancelled appointment in June, next appointment 7/26

## Slide 46: Patient #2 17y, F, white, private insurance
Attended pump class March 2024. Chose InPen
Sample (Novolog InPen) sent to family - Insulin RX sent to pharmacy, CMN/training orders started. *request sent to our pharm tech (same process for pump) and was returned "we don't follow up on InPens"
Insurance wouldn't cover Novolog, Humalog preferred - New RX for InPen and cartridges sent late April to Medtronic and pharmacy.
June – provided appointment - no mention of Inpen from provider, family or nurse (float)

## Slide 47: Patient 3 13y, F, Hispanic, public insurance
Attended pump class in March 2024. Chose InPen
InPen process started
Provider visit in May 2024 – no mention of InPen - ordered Tandem Mobi.

## Slide 48: Pain Points
Lessons Learned

## Slide 49
Met with Medtronic reps about process of ordering InPen
Added InPen slides to Insulin Pump Class
Health Fair
Added InPen brochure and contact information to our pump booklet
Process created for InPen samples in clinic
Updated process on ordering InPen
Chart: 
| sept 23 n108 | Oct 23 n108 | Nov23 n95 | Dec23 n85 | Jan24 n90 | Feb24 n105 | Mar24 n115 | Apr24 n98 | May24 n84
Measure - Rate | 0.046296 | 0.037037 | 0.021053 | 0.047059 | 0.033333 | 0.038095 | 0.0086957 | 0.020408 | 0.059524
Baseline | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
Goal | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08

## Slide 50
 | Jan | Feb | March | April | May
Middle eastern/northern african | 4 | 5 | 5 | 4 | 5
White | 43 | 50 | 59 | 46 | 37
Hispanic | 27 | 29 | 28 | 29 | 27
Decline | 3 | 1 | 2 | 2 | 2
Black | 5 | 12 | 12 | 7 | 7
Other Pacific Islander | 1 | 1 |  |  | 
Samoan Other Pacific Islander | 1 |  |  | 1 | 
Asian Indian | 2 |  |  |  | 1
Filipino White | 1 |  | 1 |  | 
Other Asian | 2 | 2 | 1 | 1 | 
White Black |  |  | 1 | 1 | 
Filipino black white |  |  | 1 | 1 | 
Black Filipino |  |  | 1 |  | 
Other Asian White |  |  |  | 1 | 
Hispanic White |  |  |  | 2 | 
White Hispanic |  |  |  | 1 | 
Black Hispanic |  |  |  |  | 2
White American Indian or Alaska Native |  |  |  |  | 
White Filipino |  |  |  |  | 1
 | 89 | 100 | 111 | 96 | 82